TADDAC Action Items from June 14, 2024

Updated: 08/26/24

Action Item #68: ONGOING

Committee members to assist CTAP and CRS Vendor outreach efforts by emailing information or reporting on community events to the DDTP Committee Coordinator.

Priority (L/M/H): Medium

Date Assigned: March 2017

Assigned To: Committee Members and Committee Coordinator

Due Date: None

Status: Ongoing

Comments on 04/26/24: Reina Vazquez encouraged Members to keep sending her community events for potential Program participation and so that other Members can find out about them. This action item is ongoing.

Action Item #76: OPEN

Katie Wright will work with the CPUC Representative to get amplified and captioned telephones for future emergency evacuation shelters throughout California.

Priority (L/M/H): Medium

Date Assigned: September 2018

Assigned To: Katie Wright

Due Date: None

Status: Open

Comments on 04/26/24: Tyrone Chin shared that he has not received any updates from the California Office of Emergency Services (Cal OES). He noted that evacuation center staff can call the Contact Center to request equipment for evacuees. Brent Jolley added that CD and CSD are working to staff the Contact Center so that consumers who have equipment needs and are dealing with natural disasters, can call the Contact Center after hours. This action item remains open.

Action Item #99: OPEN

TADDAC will make an effort to recruit new Members for its four open seats. TADDAC is seeking a Mobility Impaired, Youth, Hard of Hearing, and an At-Large Community Representative.

Priority (L/M/H): Medium

Date Assigned: January 2021

Assigned To: TADDAC

Due Date: Open until Members are selected.

Status: Open

Comments on 04/26/24: Katie Wright encouraged TADDAC to recruit for open seats as it is Members’ duty to find new members. This action item remains open.

Comments on 06/14/2024: Devva Kasnitz reported that she may have found someone who was interested in serving as a replacement for her Mobility Impaired Community Seat. This action item remains open.

Action Item #107: OPEN

Brent Jolley will provide an update regarding the MyMMXdb software and how it connects to, and works with, the Universal Telecommunications Access Platform.

Priority (L/M/H): Medium

Date Assigned: March 2023

Assigned To: TADDAC

Due Date: April 2023

Status: Open

Comments on 04/26/24: Brent Jolley shared that the MyMMXdb pilot has been approved for funding. He noted that because Bryen is dealing with some health issues, the Scope of Work for the pilot has been put on hold. This action item remains open.

Comments on 06/14/2024: There was no update at this time. This action item remains open.

Action Item #108: OPEN

TADDAC will review the Charter to understand if Members may advise CD staff on the development of Requests for Proposals (RFPs) and Invitations for Bids (IFBs) related to the Program.

Priority (L/M/H): Medium

Date Assigned: April 2023

Assigned To: TADDAC

Due Date: June 2023 September 2024

Status: Open

Comments on 04/26/24: Lisa-Marie Clark will give a presentation on the Committees’ ability to create subcommittees to advise the CPUC on future RFPs and IFBs at the May Joint Committees meeting. This action item remains open.

Comments on 06/14/24: There was no update at this time, but Legal Liaison Lisa-Marie Clark will be ready for an update in September. This action item remains open.

Action Item #109: OPEN

EPAC and TADDAC will brainstorm ideas regarding the needs of cell phone accessibility for their communities and report back to the Committees.

Priority (L/M/H): Medium

Date Assigned: May 2023

Assigned To: EPAC and TADDAC Members

Due Date: September 2023

Status: Open

Comments on 04/26/24: Reina Vazquez reported that she has received feedback from Katie Wright regarding InnoCaption. This action item remains open.

Comments on 06/14/24: Committee Coordinator, Reina Vazquez reminded Members that the purpose of this action item was for the Committees to brainstorm and email their thoughts, wishes and dreams of telecommunications equipment that maybe doesn’t yet exist, but that would make it easier for their communities to use a telephone independently. This action item remains open.

Action Item #111: OPEN

CD will consider adding cell phones to the DDTP program, especially mobile phones that are accessible for people who are mobility challenged and vision impaired.

Priority (L/M/H): Medium

Date Assigned: October 2023

Assigned To: CPUC

Due Date: November 2023

Status: Open

Comments on 04/26/24: Brent Jolley shared that States will not need to follow a recertification process with the FCC for IP-based Relay. The States have also been looking into integrating one phone number throughout all of the Relay systems through access to the ITRS database. This action item remains open.

Comments on 06/14/24: Katie Wright asked Lisa-Marie Clark if the topic of cell phones would be discussed at the public hearings. Lisa- Marie responded affirmatively that it is part of the rulemaking and encouraged Members to attend and provide their thoughts to the judge. This action item remains open.

Action Item #112: CLOSED

PPCA contractor, Maximus, and Field Operations contractor, Communications Service for the Deaf (CSD), will give a presentation to the Committees at the May Joint Committees meeting. They will introduce themselves and address roles and staffing concerns.

Priority (L/M/H): Medium

Date Assigned: March 2024

Assigned To: CPUC

Due Date: May 2024

Status: Closed

Comments on 04/26/24: Maximus and CSD will be introducing themselves and their new roles in the Program, as well as addressing concerns from Members at the May Joint Committees meeting. This action item is open.

Comments on 06/14/24: Maximus and CSD both gave presentations at the May 17th Joint Meeting. This action item is now closed.

Action Item #113: CLOSED

Brent Jolley will investigate whether or not the Committees are able to receive a presentation on the findings and recommendations posed in the Needs Assessment final report.

Priority (L/M/H): Medium

Date Assigned: March 2024

Assigned To: CD

Due Date: April 2024

Status: Closed

Comments on 04/26/24: A presentation on the Needs Assessment findings and recommendations will be given by Tyrone Chin at the May Joint Committees meeting. This action item is open.

Comments on 06/14/24: Tyrone Chin gave a presentation on the findings and recommendations posed in the Needs Assessment at the May 17th Joint Meeting. This action item is now closed.

New Action Item #114: OPEN

At the January 2023 TADDAC Meeting, Kevin Siemens suggested a policy change to Hamilton Speech-to-Speech. Users would be allowed a 2-hour window prior to an event, like a virtual meeting or class, to call and leave a message or introduction that can be saved and read aloud when needed, for long term use.

Priority (L/M/H): Medium

Date Assigned: April 2024

Assigned To: Hamilton Relay

Due Date: June 2024

Status: Open

Comments on 04/26/24: At the April 2024 TADDAC Meeting, Kevin asked that this topic be included as an Agenda Item at the June 2024 TADDAC Meeting. As there will be no June TADDAC Meeting, this Action Item was created. During the last year, Kevin and Reina have been receiving updates from Christa Cervantes during Hamilton’s process. This action item is now open.

Comments on 06/14/24: The Hamilton Speech-to-Speech Long-term Message Retention Process was on page 49 of the meeting binder. This action item remains open.